## Projects
ProjectID | ProjectName | Notes | ElectricalProgress | SSProgress | PlumbingProgress | ScreedProgress | FireSuppressionProgress | OverallProgress | ACProgress | Wall Tiles Progress | Wall Partion Progress | floortiles progress | Ceiling progress | Furniture Progress | FAFF Progress | Fire Suppersion | IT | Signage | External Work | Constraction Progress | ColdRoom Progress | Equipment Progress
1 | Adnoc Sarinah |  | 60 | 50 | 90 | 0 | 0 | 32.5 | 100 | 100 | 0 | 0 | 10 | 50 | 75 | 0 | 0 | 0 | 0 | 50 | 0 | 0

## Tasks
TaskID | ProjectID | TaskName | Duration | Weight | Progress | ParentTaskID | Category | PendingItems
1 | 1 | Hood installation | 1 | 0 | 100 |  | S/S
2 | 1 | AC | 10 | 0 | 100 |  | AC
3 | 1 | Electrical | 15 | 0 | 60 |  | Electrical
4 | 1 | Wall Tiles | 5 | 0 | 100 |  | Wall Tiles
5 | 1 | Wall Patrition | 2 | 0 | 100 |  | Furniture
6 | 1 | Water Supply | 10 | 0 | 90 |  | Plumbing
7 | 1 | Drainage | 10 | 0 | 90 |  | Plumbing
8 | 1 | Dinaing Paint | 2 | 0 | 50 |  | Constraction
9 | 1 | Dining Ceiling | 5 | 0 | 20 |  | Ceiling
10 | 1 | Kitcthen Ceiling | 2 | 0 | 0 |  | Ceiling
11 | 1 | FAFF | 5 | 0 | 75 |  | FAFF
12 | 1 | IT | 5 | 0 | 0 |  | IT
13 | 1 | Sinage | 4 | 0 | 0 |  | Signage
14 | 1 | External Work | 2 | 0 | 0 |  | External Work
15 | 1 | Fire Supperstion | 1 | 0 | 0 |  | Fire Suppression
16 | 1 | Cold Room | 2 | 0 | 0 |  | Cold Room
17 | 1 | Equipment | 1 | 0 | 0 |  | Equipment
18 | 1 | Furniture Delivery | 1 | 0 | 0 |  | Furniture
19 | 1 | Coc-Cacola Delivery | 1 | 0 | 0 |  | Equipment
20 | 1 | S/S Items Delivery | 15 | 0 | 0 |  | S/S

## Orders
OrderID | ProjectID | Company | ItemCategory | OrderStatus | LPOStatus | InvoiceCopyPath | InvoiceStatus | MissingItems | DeliveryDate | InstallationDate
1 | 1 | Himalya | Cold Room | Ordered | LPO Received |  | Not Submitted
2 | 1 | Al motqeen | S/S | Ordered | LPO Received |  | Not Submitted | SS Cladding fryer and broiler | next
3 | 1 | Nile Komal | Equipment | Ordered | LPO Pending |  | Not Submitted
4 | 1 | Wearhouse | Equipment | Ordered | LPO Received |  | 100%
5 | 1 | not specified yet | Signage | Not Ordered | Pending |  | Not Submitted
6 | 1 | Haven and Fire | Fire Suppression | Ordered | LPO Received |  | Not Submitted

## PendingWork
PendingID | TaskID | ProjectID | Description | Status | DueDate
2 | 10 | 1 | Hood clading need to fix | In Progress | 2-20-2025
3 | 13 | 1 | need to BCC permit to start the work | Pending | TBD
4 | 15 | 1 | NEED TO CALL HIM TO START THE WORK | Pending | will check
5 | 16 | 1 | under fabrication | In Progress | 24-2-2025
6 | 17 | 1 | Fryer and Broiler ready for delivery | In Progress | 21-2-2025
7 | 7 | 1 | AC Drainage | In Progress | need to be checked
8 | 3 | 1 | DB | Pending | 22/255